## WBS
Project: Setting up Email server
Task No. | Task Description | Duration | Dependency | Resources Needed | Task Status | Cost(RM) | Start Date | Estimated Completion | Finish Date
1 | Initiation | 10 Days |  |  |  |  | 2021-11-01 08:00 |  | 2021-11-10 17:00
| 1.1 Hardware requirement | [5 empty] | 2021-11-01 08:00 |  | 2021-11-02 17:00
| 1.1.1 Choosing server and routers | 2 days |  | Server | Completed | RM15000 | 2021-11-01 08:00 |  | 2021-11-02 17:00
| 1.2 Network design | [5 empty] | 2021-11-03 08:00 |  | 2021-11-10 17:00
| 1.2.1 Network topology | 2 days |  | Network simulator software (GNS3,Packet Tracer) | Completed |  | 2021-11-03 08:00 |  | 2021-11-04 17:00
| 1.2.2 VLAN/interVLAN requirement | 2 day | 1.2.1 |  | Completed |  | 2021-11-05 08:00 |  | 2021-11-08 17:00
| 1.2.3 Propose server IP address | 2 days | 1.2.2 | Server IP Address | Completed |  | 2021-11-09 08:00 |  | 2021-11-10 17:00
| 1.3 Software Requirement | [5 empty] | 2021-11-09 08:00 |  | 2021-11-10 17:00
| 1.3.1 Choosing server OS | 2 days |  | Operating System ISO | Completed | RM1000 | 2021-11-09 08:00 |  | 2021-11-10 17:00
2 | Planning | 7 days |  |  |  |  | 2021-11-11 08:00 |  | 2021-11-19 17:00
| 2.1 Electing database administrators | 1 day |  | Administrator | In progress | RM3000 | 2021-11-11 08:00 |  | 2021-11-11 17:00
| 2.2 Choosing best database relational system | 1 day |  | ERD | In progress |  | 2021-11-12 08:00 |  | 2021-11-12 17:00
| 2.3 Setting emailing protocols | 1 day |  | Email Protocol | Pending | RM2000 | 2021-11-15 08:00 |  | 2021-11-15 17:00
| 2.4 Selecting infrastructure and hardwares | [5 empty] | 2021-11-16 08:00 |  | 2021-11-19 17:00
| 2.4.1 Choose place to store servers | 2 days |  | Server base location | Pending |  | 2021-11-16 08:00 |  | 2021-11-17 17:00
| 2.4.2 Choose best servers rack | 2 days |  | Server racks | Pending | RM10000 | 2021-11-18 08:00 |  | 2021-11-19 17:00
3 | Execution | 56 days |  |  |  |  | 2021-11-22 08:00 |  | 2022-02-07 17:00
| 3.1 Installing hardware | 14 days |  | Hardware manual | Pending | RM3500 | 2021-11-22 08:00 |  | 2021-12-09 17:00
| 3.2 Installing software | 7 days | 3.1 | Software installation guide | Pending | RM2500 | 2021-12-10 08:00 |  | 2021-12-20 17:00
| 3.3 Server Hardening | 7 days | 3.2 | Manual | Pending | RM2000 | 2021-12-21 08:00 |  | 2021-12-29 17:00
| 3.4 Improve site performance | 28 days |  | Network engineer | Pending | RM5000 | 2021-12-30 08:00 |  | 2022-02-07 17:00
4 | Control | 15 days |  |  |  |  | 2022-02-08 08:00 |  | 2022-02-28 17:00
| 4.1 Maintenance | [5 empty] | 2022-02-08 08:00 |  | 2022-02-25 17:00
| 4.1.1 Monthly maintainance | 7 days |  | CMMS | Pending | RM2500 | 2022-02-08 08:00 |  | 2022-02-16 17:00
| 4.1.2 Check server integrity | 4 days |  | CMMS | Pending |  | 2022-02-17 08:00 |  | 2022-02-22 17:00
| 4.1.3 Security check up | 3 days |  | SIEM (qradar) | Pending | RM3000 | 2022-02-23 08:00 |  | 2022-02-25 17:00
| 4.2 Regular backup | 1 day |  | Comet Backup | Pending |  | 2022-02-28 08:00 |  | 2022-02-28 17:00
5 | Closing | 9 days |  |  |  |  | 2022-03-01 08:00 |  | 2022-03-11 17:00
| 5.1 Presentation | 1 day |  | Documentation | Pending |  | 2022-03-01 08:00 |  | 2022-03-01 17:00
| 5.2 Report & Calculate all costs | 7 days |  | Documentation | Pending |  | 2022-03-02 08:00 |  | 2022-03-10 17:00
| 5.3 Document closeout | 1 day |  | Documentation | Pending |  | 2022-03-11 08:00 |  | 2022-03-11 17:00