## WBS
Intrusion Detection System Implementation
Task No. | Task Description | Duration | Dependency | Resources Needed | Task Status | Cost(RM) | Start Date | Estimated Completion | Finish Date
1 | Specification | 2 Days
1.1 | Specify the Network Topology required by project | [5 empty] | 2021-11-17 |  | 2021-11-18
1.2 | Identify the devices that needs to be monitored by IDS |  |  | Systems, network routers, databases |  |  | 2021-11-17 |  | 2021-11-18
1.3 | Identify risks of attacks and protection of sensitive data | [5 empty] | 2021-11-17 |  | 2021-11-18
1.4 | Gather a team to implement the project | [5 empty] | 2021-11-18 |  | 2021-11-19
1.5 | Define the approach of implementing IDS (Behavioral/Scenario based) |  |  | Network Technician and Expert |  |  | 2021-11-18 |  | 2021-11-19
2 | Implementation | 4 Days
2.1 | Choose a detector for the IDS |  |  | Solarwinds Security Events Manager |  | 200 | 2021-11-19 |  | 2021-11-23
2.2 | Install Antivirus Internet Security with intrusion detection on system |  | 2.1 |  |  |  | 2021-11-19 |  | 2021-11-23
2.3 | Install Network Intrusion System on server | [5 empty] | 2021-11-19 |  | 2021-11-23
2.4 | Install Network Intrusion Detector on system |  |  | Snort |  |  | 2021-11-19 |  | 2021-11-23
3 | Testing | 3 Days
3.1 | Scan ports for vulnerability |  |  | Burp Suite |  | 100 | 2021-11-23 |  | 2021-11-24
3.2 | Perform a simulated attack |  | 3.1 | Security Expert |  |  | 2021-11-23 |  | 2021-11-24
3.3 | Analyse the test outcome and patch vulnerabilities |  | 3.2 |  |  |  | 2021-11-24 |  | 2021-11-26
4 | Maintenance | Ongoing
4.1 | Monitor event logs acquired by the IDS |  |  | IT Security Team
4.2 | Respond to events and keep IDS up to date